## Step List
Urgency
Rating | Activities | Potential iterations
Mainly about adaptive processes
GOLD | Dismantle fixed performance contracts
Withdraw budget comparison reports
Stop doing comparisons of performance with budgets
Stop preparing budgets
Stop rewarding people on the basis of fixed performance contracts
GOLD | Revise evaluation and rewards | Using information currently available, then again once better information is available
Revise written instructions for individual performance evaluations
Revise forms for individual performance evaluations
Identify information required
Set up process for getting required information
Design formula for rewards
Agree formula for rewards
Provide training if necessary for new evaluation process
Start using new individual performance evaluation methods
Start paying by new formula
Stop paying by old method
GOLD | Revise action planning processes | Before and after decentralisation
Write new action planning process
Create forms or spreadsheets needed for new planning processes
Provide training as required
Start using new action planning process
Stop using old action planning process
GOLD | Revise strategy formation processes | Before and after decentralisation
Write new process for high level direction setting
Agree new process for high level direction setting
Start using new process for high level direction setting
Stop using old processes for high level strategy formation
SILVER | Improve KPIs | KPIs available now, the KPIs available with development effort
Clarify strategy/critical success factors/etc
Choose improved sets of KPIs
Validate causal model between KPIs
See what information is available
Set up process for getting required information
GOLD | Redesign management information packs
Redesign management information packs to show time series
Redesign management packs to show forecasts
Redesign management packs to show league tables
GOLD | Produce league tables | Different levels and KPIs, pre- and post-decentralisation
Design league table reports
Devise overall performance formula
Devise handicapping system
Set up process for producing league table reports
Set up process for gathering external benchmark data
Begin producing league table reports
Set up process for distributing league table reports
Start using league table reports for monitoring performance
BRONZE | Redesign products | By product area
Redesign products to be modular and tailorable at unit level
Begin to make products available in modular form
Communicate products
Begin selling products in modular form
BRONZE | Analyse costs | Initial analysis costly but invaluable; make later runs slicker
Model how activities generate costs
Gather data to calculate activity based costs
Calculate costs
Calculate unit profitability
Calculate customer profitability
Provide training as needed
Use data in internal market
Make data available for decision making
SILVER | Revise forecasting methods | Crude single point estimates, then outcome distributions
Devise new forecasting method
Trial new forecasting method
Decide who will see and use the forecasts, and how
Communicate about imminent availability of forecasts
Begin generating and providing forecasts
SILVER | Revise management meetings | Different levels of management
Identify types of meeting currently happening
Decide what meetings should change and how
Redesign these meetings
Workshops to rehearse new behaviours - no fixed-target talk!
Agree on new meetings
Start doing new meetings
Stop doing meetings now superceded
GOLD | Uplift financial monitoring procedures | With existing IT systems, then with improved IT systems
Survey available financial and non-financial information
Devise monitoring procedures with light touch alerts to managers
Training/development group as needed
Start providing monitoring and alerts
Stop previous procedures requesting written explanations etc
SILVER | Increase information availability | With existing IT systems, then with improved IT systems
Devise ways to make information available
Introduce improvements to noticeboard information
Introduce improvements to email information
Introduce improvements to online information
BRONZE | Make other IT improvements | N/A These are usually massive projects
Implement more customer centric IT
Use ERP to focus on processes
SILVER | Adapt and uplift risk managment
Explain model to risk management people in organisation
Review style of risk management and redesign
Rewrite description of internal controls in annual report
Mainly about decentralisation
SILVER | Devolve decision authority | In stages, and also before and after reorganising
Write new decision authority rules
Agree new decision authority rules
Training to enable people to take decisions themselves
Communicate new decision authority rules
Switch over to new decision authority rules
SILVER | Change approvals process for capital expenditure/projects | At different levels/scales of investment
Write new approvals process
Design any new forms or spreadsheets needed for new approvals process
Start using new approvals process
Stop using old approvals process
SILVER | Create/strengthen governance framework | Likely to go through more than one version/expansions
Draft governance framework: values, rules, etc
Agree governance framework
Communicate governance framework
Withdraw rules superceded by new governance framework
SILVER | Reorganise | Due to systems support, internal market may be crude initially, the redesigned
Design new organisation with smaller units, flatter structure, central services
Agree new organisation structure
Appoint people to positions in new structure
Training for new roles as needed
Reorganise into new structure with more, smaller units
BRONZE | Create internal market | Simple initially, more accurate when IT support improves
Design internal market
Agree internal market rules
Explanations/training as needed
Agree internal market rate negotiation process
Agree internal market rates
Get IT systems to support internal market
SILVER | Customer allocation | Simple initially, more accurate when IT support improves
Allocate customers to business units/branches
Agree rules for accounting for sales to customers
Communicate new arrangements
Get IT systems to support rules for accounting for sales
BRONZE | Set up Service Level Agreements | Pre- and Post-reorganisation
Identify services for which agreements needed
Devise means of monitoring service level performance
Design process for agreeing SLAs
Agree SLAs
Begin operating new SLAs
Dismantle any superceded procedures or agreements
BRONZE | Create a process for assimilating new acquisitions
Review a recent acquisition to clarify issues
Write a process for extending the management model to new acquisitions
Agree the process
Included it with other process documents
Revise after use
General tasks including project management
GOLD | Project management | These are repeated throughout
Organise team
Obtain resources
Benefits review with stakeholders
Progress reporting
Planning and risk management
Assess and report benefits to date
GOLD | Communicate about the new model | Probably a phased communication plan
Devise clear written explanation of the model and values behind it
Test the explanation for clarity and intended impact
Communicate
Identify people who need special attention
Organise events to engage key people
Hold events with key people
GOLD | Obtain assurance | Also likely to be phased
Discuss plans with Internal Audit and agree programme of reviews
Forewarn external auditors of plans and help them adapt audit approach
Respond to audit issues raised
Regularly liaise with internal auditors
Support external auditors as required